Appendix B:

| Challenge Management - Timelines |  |  |  |
| --- | --- | --- | --- |
| DAY | DESIGN PROCESS | # ACTIVITY | NOTES |
| 1 | Project Introduction Research Information Gathering | - Introduction of project - Location of Resources/Collaboration Systems/ - Discuss order of Procedure - Discuss Group Formation | - Location of all Project Files - Encourage BOD (Bring Your Own Device), Google Groups, Review/Communication of group member methods |
| 2 |  | - Students form groups of 2 - Review Activity – Challenge Requirements - Introduce Technical Reporting – Engineering Log Requirements - Review order of Procedure - Graphic Organizer and Gantt chart lesson - Complete situation | - Outline Engineering Log Requirements and Sample noting - Evaluation – Challenge Requirements - Review Google Classroom - Location of all Project Files - Setup up Project Management/Gantt Chart |
| 3 |  | - Graphic Organizer and Gantt chart lesson - Lesson/review of Hydraulics/Pneumatics - Investigate simple machines - Begin Investigation - Brainstorming of ideas | - Research hydraulic and actual Pick N’ Place principles and examples. |
| 4 |  | - Review Technical Drawing Methods (thumbnail sketching, sketching to scale) | - Technical Drawing Exercises if necessary |
| 5 |  | - Investigation – Research - Brainstorming – Thumbnails of Ideas | - Work Period – Complete for Homework |
| 6 | Project Developing Selecting Best Solution | - Review Technical Drawing Methods (thumbnail sketching, sketching to scale) - 2 concept/thumbnail sketches (individual) - Gantt Chart Review - DUE | - Instructor to review Project Management/Gantt Charts - Complete for homework |
| 7 |  | - Review Technical Drawing Methods - 2 thumbnail sketches (per individual due) - 2 concept sketches to scale (individual) | Complete for homework Submit Thumbnails |
| 8 |  | - 2 concept sketches to scale (individual) DUE | Submit Concept Scale Sketches |
| 9 |  | - Review CAD drawing requirements - Proper Title Pages – Set up Drawings - Ongoing process – Update CAD drawings to Evaluation Documentation Project Portfolio Stage Activities | AutoCAD, Google Sketchup |
| DAY | DESIGN PROCESS | # ACTIVITY | NOTES |
| 10 |  | - CAD Drawings - Prepare Bill of Material | DO NOT ASK FOR MATERIALS UNTIL ALL TASKS ARE COMPLETE TO THIS POINT |
| 11 | Tool Safety | Hand/Power tools safety and correct method of Use to be covered but not exclusive: - Dremel Tool - Drill Press - Hand Saw - Mitre Saw - Scroll Saw - Modelling Knives (Exacto) - Hot Glue Gun - Paints Sealants and Finishes | - Student sign off on tools - Safety Test |
| 13 | Modelling Construction | - Students building projects |  |
| 14 |  | - Students building projects |  |
| 15 |  | - Students building projects |  |
| 16 |  | - Students complete building projects - Begin CAD drawings |  |
| 17 | Evaluation Documentation | - CAD drawing | NO SHOP WORK |
| 18 |  | - Test projects |  |
| 19 |  | - Complete CAD and Paperwork | TECH REPORT DUE IN TWO CLASSES |
| 20 |  |  |  |