APPENDIX B:  GANTT Chart Example of a Park Design (To be adapted as needed)

Proposed Work Schedule

| Phase | Key Tasks | Pre-Project | February | March | April | May | June |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project | Contract |  |  |  |  |  |  |
| Start-Up | Workplan |  |  |  |  |  |  |
|  | Documents |  |  |  |  |  |  |
|  | Notices |  |  |  |  |  |  |
| Phase 1 | Assessment |  |  |  |  |  |  |
| (Technical) | Site Review |  |  |  |  |  |  |
|  | Mapping |  |  |  |  |  |  |
|  | Constraints |  |  |  |  |  |  |
|  | Opportunities |  |  |  |  |  |  |
|  | Analysis |  |  |  |  |  |  |
|  |  |  | ▲ |  |  |  |  |
| Phase 2 | Meetings |  |  |  |  |  |  |
| (Public | Focus Group |  |  |  |  |  |  |
| Input) | Workshop |  |  |  |  |  |  |
|  | Open House |  |  |  |  |  |  |
|  | Communication |  |  |  |  |  |  |
|  |  |  |  |  |  |  | ▲ |
| Phase 3 | Preliminary |  |  |  |  |  |  |
| (Plan | Concepts |  |  |  |  |  |  |
| Preparation) | Review |  |  |  |  |  |  |
|  | Revise |  |  |  |  |  |  |
|  | Open House |  |  |  |  |  |  |
|  | Final Plan |  |  |  |  |  |  |
|  | Report |  |  |  |  |  |  |
|  | Council |  |  |  |  |  |  |
|  |  |  |  |  |  |  | ▲ |

▲  Denotes Milestone – Completion of Phase

Proposed Staffing

| Phase | Key Tasks | Staffing | Time Allocation | Estimated Hours |
| --- | --- | --- | --- | --- |
| Project Start –Up | Workplan, Documents | (Project Manager) | 2.0 days | 7 |
| Technical Review | Mapping | Staff 1,Staff 2,Staff 3 | 3.0 days | 21 |
|  | Site Analysis |  | 3.0 days | 21 |
| Public Consultation | Focus Groups |  | 3.0 days | 42 |
|  | Workshop |  | 1.0 days | 14 |
|  | Open House |  | 1.0 days | 14 |
|  | Communications |  | 1.0 days | 7 |
| Plan Preparation | Concepts |  | 3.0 days | 21 |
|  | Review - Revisions |  | 2.0 days | 28 |
|  | Report |  | 2.0 days | 21 |
|  | Council |  | 1.0 days | 7 |
|  |  |  | Project Management | 21 |
|  |  |  | Designer/Planner | 100 |
|  |  |  | Technologist | 77 |